## Sheet1
Date | Name | Since last meeting | Before next meeting | Blockers
22/12/17
| Jude | went through the diagrams. Started to write the algorithms for the very first flow chart provided by miss | finish the basic algorithm for the first flow chat | None
| Sajith | learned AODV, ns-3, DT, IT and research paper. All were just upto some extent. | hope to dual boot machine with Ubuntu because old laptop had some issues in Ubuntu | None
| Sandunika | went through the diagrams. | complete first pseudo code. | UEE final project
| Anushka | Went through the flow chart on direct trust calculation and went through the research paper. | Work on the algorithm for the first flow chart. Look up on reinforcement learning. | Had to work on the UEE project submission which is due tomorrow (23rd Saturday)
23/12/17
| Jude | went through the remaining algorithm | write the completed pseudo code | None
| Sajith | went through research paper | start writing psuedocodes | None
| Sandunika | wrote the first pseudo code | complete pseudo codes for 2nd and 3rd algorithms and watched videos given by sir | None
| Anushka | Worked on the algorithm for the first flow chart, went through the research paper more and looked up on reinforcement learning | finish the pseudo code for the first flow chart, look up on Q-learning | None
24/12/17
| Jude | Had a meeting with all group members to discuss about the algorithms and finalized those | there is one last psudocode remaining for "After transmission phase"; need to complete it | there are some minor points I encounted while writing some algorithms. Need to get clasrified those
| Sajith | watched some ns3 videos. Discussed and wrote some psuedocodes | After transmission phase psuedocode has to complete | need to clarify flow chart doubts
| Sandunika | watch some python videos. Read Q learning research paper | Learn more about AD Hoc networks Go through research paper more | none
| Anushka | Helped with writing the pseudo code for for first , second and third flowcharts. Started working on the pseudo code for the fourth flowchart. | finish the pseudo code for the fourth flow chart. Go through machine learning videos | While writing the algorithms. Came across points which need further clarification.
25/12/17
| Jude | I couldn't do any work today, as I was busy with Christmas celebration all around me | help to refine the 4th pseudo code and complete it | Clarifications need to get from Chamira miss about what we have raised yesterday
| Sajith | wrote last psuedocode | ns3 implementation stuff need to go through | had an outing
| Sandunika | went through research paper | go throught python videos | none
| Anushka | Wrote the algorithm for the fourth flowchart (Not perfect yet). Watched some Python tutorials. | Finalize the algorithm for the last flow chart. Watch further tutorials on related topics. | Came across some doubtful areas in the last flowchart.
26/12/17 | Jude | Went through the old diagrams and check if there are any further improvements | complete the 4th pseudo code, Modify the old diagrams according to the answers for our questions we had | None
| Sajith | set up the environment for run ns3, went through the answers by sir and miss | complete psudocodes | none
| Sandunika | watch some python videos | go through research papers | none
| Anushka | Got Ubuntu installed Went through the answers provided for the issues we had | Finalize algorithms | none
27/12/17 | Jude | Went through some of the machine learning tutorials, had a samll discussion about the 4th psudocode | find out the problems within the existing psudocodes and try to make them correct if we could find any faults. | None
| Sajith | play around with ns3, went through the last psudocode which was discussed yesterday | need to move bit depth in psudocodes plus ns3 | none
| Sandunika | installed ubuntu, wenr through 4th psudocode | go through ns3 installing process | none
Anushka
28/12/17 | Jude | Went through the pseudo codes and tried to clear out the doubts , participated for the meeting with the supervisor and discussed more about the written pseudo codes and get verified by them | Do the modifications for those pseudo codes with the teammates, start making the document about the the algorithms we have written with some explainations | none
| Sajith | went through the diagrams with new modifications | go through IT calculation and design diagram with teammates, start documenting | none
| Sandunika | none (had a busy day at work. I'll cover extra work tomorrow. ) | go through ns3 installation procesd. Work on pseudo codes | none
| Anushka | Went through the content of the discussion took place today with the supervisor | Make the necessary changes to the algorithms and finalize them | none
29/12/17 | Jude | Start going through the research papers and trying to understand the remaining model | finalize the 4th pseudo code, Finalize the other 3 codes, Read the research papers | None
| Sajith | wrote 4th psudocode | complete documenting | None
| Sandunika | Write the pseduo code for modified 4th diagram | Complete the Q learning research paper | none
Anushka
30/12/17 | Jude | refined the after transmission phase pseudo code, installed the visual studio IDE, started to write transmission code in C++, prepared the document which includes all 4 pesudo codes with a description of what each code does (as a group work) | finalize the document content, read and understand about the research papers in-depth, write the remaining C++ codes | None
| Sajith | started to write spiral code in C++, prepared the doc as a team work | read the research paper to get a more idea about the IT calculation process | None
| Sandunika | started to write DT calculation code in C++, participated for documentation | go through research paper, complete c++ code | none
| Anushka | Wrote the pseudo code for identifying trust levels according to the research paper standard, Started the c++ coding for identifying trust levels for a node, Did the documentation part for identifying trust levels | Install NS3 , Complete the c++ code | None
31/12/17 | Jude | Read the first research paper, Had a discussion with other members about the second research paper | finish the remaining section in the research papers, Write C++ codes | None
| Sajith | Read the second research paper, Had a discussion with other members regarding first research paper | Finish reading the second research paper, Continue c++ code | None
Sandunika
Anushka