## Sheet1
Date | Name | Since last meeting | Before next meeting | Blockers
22/12/17
| Jude | went through the diagrams. Started to write the algorithms for the very first flow chart provided by miss | finish the basic algorithm for the first flow chat | None
| Sajith | learned AODV, ns-3, DT, IT and research paper. All were just upto some extent. | hope to dual boot machine with Ubuntu because old laptop had some issues in Ubuntu | None
| Sandunika | went through the diagrams. | complete first pseudo code. | UEE final project
| Anushka | Went through the flow chart on direct trust calculation and went through the research paper. | Work on the algorithm for the first flow chart. Look up on reinforcement learning. | Had to work on the UEE project submission which is due tomorrow (23rd Saturday)
23/12/17
| Jude | went through the remaining algorithm | write the completed pseudo code | None
| Sajith | went through research paper | start writing psuedocodes | None
| Sandunika | wrote the first pseudo code | complete pseudo codes for 2nd and 3rd algorithms and watched videos given by sir | None
| Anushka | Worked on the algorithm for the first flow chart, went through the research paper more and looked up on reinforcement learning | finish the pseudo code for the first flow chart, look up on Q-learning | None
24/12/17
| Jude | Had a meeting with all group members to discuss about the algorithms and finalized those | there is one last psudocode remaining for "After transmission phase"; need to complete it | there are some minor points I encounted while writing some algorithms. Need to get clasrified those
| Sajith | watched some ns3 videos. Discussed and wrote some psuedocodes | After transmission phase psuedocode has to complete | need to clarify flow chart doubts
| Sandunika | watch some python videos. Read Q learning research paper | Learn more about AD Hoc networks Go through research paper more | none
| Anushka | Helped with writing the pseudo code for for first , second and third flowcharts. Started working on the pseudo code for the fourth flowchart. | finish the pseudo code for the fourth flow chart. Go through machine learning videos | While writing the algorithms. Came across points which need further clarification.
25/12/17
| Jude | I couldn't do any work today, as I was busy with Christmas celebration all around me | help to refine the 4th pseudo code and complete it | Clarifications need to get from Chamira miss about what we have raised yesterday
| Sajith | wrote last psuedocode | ns3 implementation stuff need to go through | had an outing
| Sandunika | went through research paper | go throught python videos | none
| Anushka | Wrote the algorithm for the fourth flowchart (Not perfect yet). Watched some Python tutorials. | Finalize the algorithm for the last flow chart. Watch further tutorials on related topics. | Came across some doubtful areas in the last flowchart.