## Sheet1
Date | Name | Since last meeting | Before next meeting | Blockers
22/12/17
| Jude | went through the diagrams. Started to write the algorithms for the very first flow chart provided by miss | finish the basic algorithm for the first flow chat | None
| Sajith | learned AODV, ns-3, DT, IT and research paper. All were just upto some extent. | hope to dual boot machine with Ubuntu because old laptop had some issues in Ubuntu | None
| Sandunika | went through the diagrams. | complete first pseudo code. | UEE final project
| Anushka | Went through the flow chart on direct trust calculation and went through the research paper. | Work on the algorithm for the first flow chart. Look up on reinforcement learning. | Had to work on the UEE project submission which is due tomorrow (23rd Saturday)
23/12/17
| Jude | went through the remaining algorithm | write the completed pseudo code | None
| Sajith | went through research paper | start writing psuedocodes | None
| Sandunika | wrote the first pseudo code | complete pseudo codes for 2nd and 3rd algorithms and watched videos given by sir | None
| Anushka | Worked on the algorithm for the first flow chart, went through the research paper more and looked up on reinforcement learning | finish the pseudo code for the first flow chart, look up on Q-learning | None
24/12/17
| Jude | Had a meeting with all group members to discuss about the algorithms and finalized those | there is one last psudocode remaining for "After transmission phase"; need to complete it | there are some minor points I encounted while writing some algorithms. Need to get clasrified those
| Sajith | watched some ns3 videos. Discussed and wrote some psuedocodes | After transmission phase psuedocode has to complete | need to clarify flow chart doubts
| Sandunika | watch some python videos. Read Q learning research paper | Learn more about AD Hoc networks Go through research paper more | none
| Anushka | Helped with writing the pseudo code for for first , second and third flowcharts. Started working on the pseudo code for the fourth flowchart. | finish the pseudo code for the fourth flow chart. Go through machine learning videos | While writing the algorithms. Came across points which need further clarification.
25/12/17
| Jude | I couldn't do any work today, as I was busy with Christmas celebration all around me | help to refine the 4th pseudo code and complete it | Clarifications need to get from Chamira miss about what we have raised yesterday
| Sajith | wrote last psuedocode | ns3 implementation stuff need to go through | had an outing
| Sandunika | went through research paper | go throught python videos | none
| Anushka | Wrote the algorithm for the fourth flowchart (Not perfect yet). Watched some Python tutorials. | Finalize the algorithm for the last flow chart. Watch further tutorials on related topics. | Came across some doubtful areas in the last flowchart.
26/12/17 | Jude | Went through the old diagrams and check if there are any further improvements | complete the 4th pseudo code, Modify the old diagrams according to the answers for our questions we had | None
| Sajith | set up the environment for run ns3, went through the answers by sir and miss | complete psudocodes | none
| Sandunika | watch some python videos | go through research papers | none
| Anushka | Got Ubuntu installed Went through the answers provided for the issues we had | Finalize algorithms | none
27/12/17 | Jude | Went through some of the machine learning tutorials, had a samll discussion about the 4th psudocode | find out the problems within the existing psudocodes and try to make them correct if we could find any faults. | None
| Sajith | play around with ns3, went through the last psudocode which was discussed yesterday | need to move bit depth in psudocodes plus ns3 | none
| Sandunika | installed ubuntu, wenr through 4th psudocode | go through ns3 installing process | none
Anushka
28/12/17 | Jude | Went through the pseudo codes and tried to clear out the doubts , participated for the meeting with the supervisor and discussed more about the written pseudo codes and get verified by them | Do the modifications for those pseudo codes with the teammates, start making the document about the the algorithms we have written with some explainations | none
| Sajith | went through the diagrams with new modifications | go through IT calculation and design diagram with teammates, start documenting | none
| Sandunika | none (had a busy day at work. I'll cover extra work tomorrow. ) | go through ns3 installation procesd. Work on pseudo codes | none
| Anushka | Went through the content of the discussion took place today with the supervisor | Make the necessary changes to the algorithms and finalize them | none
29/12/17 | Jude | Start going through the research papers and trying to understand the remaining model | finalize the 4th pseudo code, Finalize the other 3 codes, Read the research papers | None
| Sajith | wrote 4th psudocode | complete documenting | None
| Sandunika | Write the pseduo code for modified 4th diagram | Complete the Q learning research paper | none
Anushka
30/12/17 | Jude | refined the after transmission phase pseudo code, installed the visual studio IDE, started to write transmission code in C++, prepared the document which includes all 4 pesudo codes with a description of what each code does (as a group work) | finalize the document content, read and understand about the research papers in-depth, write the remaining C++ codes | None
| Sajith | started to write spiral code in C++, prepared the doc as a team work | read the research paper to get a more idea about the IT calculation process | None
| Sandunika | started to write DT calculation code in C++, participated for documentation | go through research paper, complete c++ code | none
| Anushka | Wrote the pseudo code for identifying trust levels according to the research paper standard, Started the c++ coding for identifying trust levels for a node, Did the documentation part for identifying trust levels | Install NS3 , Complete the c++ code | None
31/12/17 | Jude | Read the first research paper, Had a discussion with other members about the second research paper | finish the remaining section in the research papers, Write C++ codes | None
| Sajith | Read the second research paper, Had a discussion with other members regarding first research paper | Finish reading the second research paper, Continue c++ code | None
Sandunika
Anushka
2018-01-01 | Jude | I couldn't do much work except reading the remaining pages of the 1st research paper | Finish reading papers, Have a discussion with the other members, Try to come up with a flowchart for indirect trust calculation | None
| Sajith | read the research paper | start coding | None
| Sandunika | complete the Q-learning research paper, Go through some c++ tutorials | complete second research paper | none
| Anushka | Went through the research papers | Go through research papers more , Go through NS3 tutorials | None
2018-02-01 | Jude | Went through the research paper, Wrote some remaining section of the 4th algorithm in C++ | Come up with a sketch for the indirect trust calculation | None
| Sajith | went through C++ video | complete spiral C++ code | None
| Sandunika | complete the Q-learning research paper, Go through some c++ tutorials | read research paper, Go through c++ tutorials | none
| Anushka | Went through the research papers, went through NS3 tutorials | Complete the c++ codes | None
2018-03-01 | Jude | Went through the C++ codes, Started the discuss about the 2nd research paper within the group | Finish reading the 2nd research paper, Have an Google hangout session for the introduction of the NS3 codebase | None
| Sajith | went through C++ tutorials | complete C++ code | None
| Sandunika | start writing c++ code, Went through research paper | read research papers, Complete c++ code | none
| Anushka | Went through the discussion notes noted by the group about Axioms | Complete the c++ codes, Go through the tutorials | None
2018-04-01 | Jude | Discussed about the 4 aximos and the 2 models proposed by the 2nd research paper | have the NS3 introductory session about the module structure | None
| Sajith | started C++ implementing | go through ns3 tutorials | none
| Sandunika | Watched c++ tutorials, Study aout 4 axioms | Complete c++ code, read research papers | none
| Anushka | Went through c++ tutorials and implemented most of the code | Complete the c++ code | none
2018-05-01 | Jude | Went through the remaining section in second research paper, Did a introductory session for ns3 | Watch the NS3 YouTube videos, Start to getting familiarize with ns3 code | None
| Sajith | Implementation completed upto some extent | Watch NS3 tutorials | None
| Sandunika | Completed c++ code for DT calculation | watch ns3 tutorials, Read research paper | none
| Anushka | Started watching NS3 tutorials, Changed the implemented c++ code for algorithm 2 by including classes | Watch NS3 tutorials | none
2018-06-01 | Jude | Started to watch the YouTube video series, Built a small network topology along with the tutorial guide | Watch the aodv videos, Get basic idea about NS3 classes for creating a small network | None
| Sajith | went through ns3 tutorials | get an idea about ns3 project structure | None
| Sandunika | watched ns3 tutorials | Cotinue watching ns3 tutorials | none
| Anushka | Watched NS3 tutorials, Made more changes to the implemented c++ code | Watch more NS3 tutorials, Finalize the changed c++ code | None
2018-07-01 | Jude | Watched the youtube videos about ns3, created a small network topology by following up those tutorial series, started to observe a bit about the aodv module folder in ns3 | Do another hangout session with the findings in the aodv module code in ns3 | None
| Sajith | Went through ns3 | Fix building issues of migrating from ns3.26 to ns3. 20 | None
| Sandunika | watched ns3 tutorials, Went through ns3 installation process further | successfully install ns3, Build network by following tutorials | none
| Anushka | Went through AODV and gathered information to be presented on the next hangout session | Get more familiar with NS3, Explain about AODV to the rest of the members | none
2018-08-01 | Jude
| Sajith | Fixed the build issue of migrating from ns3. 26 to ns3. 20, Created a network topology upto some extent | Go through ns3 ahead | none
Sandunika
| Anushka | Installed the suggested version of NS3 successfully and went through it, Watched an NS3 tutorial and tried it on | Try out more tutorials on NS3 and get familiar with it | None
2018-09-01 | Jude | Started to look into the aodv prototal code implementations | provide an feedback to sir with the investigation findings on existing aodv protocol implementation | None
| Sajith | Went through ns3 tutorials, Went through project structure a bit | Configure things according to our research project | None
| Sandunika | tried out ns3 tutorails | find more ns3 tutorials and try them | none
| Anushka | Watched more NS3 tutorials and tried them | Keep on watching more tutorials and try them, Look further in to adding applications | None
2018-10-01 | Jude | Went through the aodv protocol example, Identified some class flows | Do a hangout session about the class structures which related to aodv protocol | None
| Sajith | Went through AODV module in ns3 | Try to find the place where we should call our implemented c++ code last week | none
| Sandunika | Went through aodv prototal code implementations | Go through the aodv code further and try to understand unclear parts | none
| Anushka | Went through AODV module in the NS3 code | Try to figure out where to make the decision when sending packets | None
2018-11-01 | Jude | Went through the code and identified how a protocol is being plugged to a simulation | Do the google hangout session about the knowledge gathered so far, Continue to surf in the ns3 code | None
| Sajith | Played around with aodv.cc | Go through ns3 code moreover | None
Sandunika
| Anushka | Went through AODV example class and other references and tutorials. | Participate to the session and Learn how the protocol plugs ins to a simulation, Go through AODV more | None
2018-12-01 | Jude
| Sajith | Got an idea about aodv sample file | Go through dsdv sample file get more idea about aodv | None
| Sandunika | Went through AODV sample files | Go through the code more and have an idea about dsdv files | none
| Anushka | Participated in the AODV hangout session and got an idea about it, Went through the video again | Check out dsdv and dsr files as well. | None
13/1/2018 | Jude | Went theough the Scheduler engine in NS3, Went through the code examples | Start writing the new protocol file | As the scheduler engine is more complex when it comes to identifying the overall procedure, decided to move on implementation
| Sajith | Went through ns3 documentations | Start implementing in ns3 | None
| Sandunika | went through ns3 code examples and documentation | start implementations | none
Anushka
14/1/2018 | Jude | Went through the code and started to create a new protocol file and tried to test it | Resolve the existing problem with ping is not being working with the new protocol file | None
| Sajith | Experimented aodv sample file | Create a new module in ns3 and try out | None
| Sandunika | went through the aodv helper classes more | Try to create the new protocol file | none
Anushka
15/1/2018 | Jude | Went through the errors encountered while building the module and fixed them, Explained the current progress to all members and clarified the doubts, Posted a new post on ns3 Google group about the gsoc 2018 which related to this project | Observe the existing routine table interactions and try to figure out a way to implement the trust table | None
| Sajith | Created a new module in ns3 which is same as aodv with team mates | Start coding in new module | none
Sandunika
| Anushka | Went through the added new NS3 module, Went through the code with the group members and discussed | Figure out how routing table works, Try to implement the code inside the new module | none
16/1/2018 | Jude | went through the gsoc document pages on ns-3 and posted a new thread about the project | have a group discussion and try to write a new pseudo code and algorithm for indirect trust calculation | None
| Sajith | Started coding in aodv-trust module | Finalize the algorithm to calculate Indirect Trust | None
| Sandunika | went through aodv trust module part, Went through indirect trust calculation | write algorithm for indirect trust calculation | none
| Anushka | Worked on the flow chart of calculating indirect trust. | Implement the pseudo code and the documentation for calculating the indirect trust. | none
17/1/2018 | Jude | Constructed the indirect trust calculation flow chart with other members, Drew the pseudo code for the above flow chart with other members | Check the current progress of the indirect trust calculation and finish it, Check the trust table implementation inside ns-3 | None
| Sajith | Started C++ implementation | Complete the implementation of indirect trust calculation | none
| Sandunika | went through the printing routing tables code | go through the direct trust implementation | none
| Anushka | Had a discussion with the group to implement the pseudo code and the c++ code for calculating the indirect trust, Went through the completed pseudo code and tried to implement the code with c++ | Do the documentation for calculating the indirect trust | none
18/1/2018 | Jude | discussed and formulated the way to calculate the indirect trust with other group members, created the pseudo code for that and flow chart | do the modification for TRR message in pseudo code and flowchart, start the implementation for that algo in C++ (not in ns-3) | None
| Sajith | Implemented algorithm with team members | TRR message passing algorithm need to be done | None
Sandunika
| Anushka | Did the documentation for calculating the indirect trust | Discuss with the group and do the necessary modification with the group for the indirect trust calculation | none
19/1/2018 | Jude | had a group discussion and helped to resolve the existing problems with Indirect trust calculation C++ code | go through the research paper with team mates and write the pseudo code and the algo | None
| Sajith | Clarified some doubts related to TRR | Come up with an algorithm for TRR | none
| Sandunika | went through the TRR messaging process | write pseudo code and algorithm for TRR | none
Anushka
20/1/2018 | Jude
| Sajith | Modified the way of calculating IT algorithm | Complete modified algorithm | none
| Sandunika | went through the modified IT calculations | Complete pseudo code according to the modified calculations | none
| Anushka | Went through the modified method of calculating indirect trust | Help with implementing the modified algorithm | None
21/1/2018 | Jude | Discussed about the modifications suggested to the Indirect trust calculation procedure, modified the pseudo code with the help of others, fine tuning the code which chamara has wrote for this new modified version in C+ | Solve the existing problem in the C++ code, start look into the ns-3 source code and plan the implementation | None
| Sajith | Implemented the algorithm for new IT calculation in C++ with team members | Continue the implemention in ns3 | None
| Sandunika | Participated for the pseudo cide modifications, Went through the modified c++ code | do the implementations | none
Anushka
22/1/2018 | Jude
| Sajith | Integrated direct trust calculation project with indirect trust calculation project. | Complete the c++ project | none
| Sandunika | integrated the direct trust c++ code to the project | solve problems and complete the direct trust implementation c++ code | none
| Anushka | Added a c++ project to TFS for everyone to code their part, Started coding on the added project. Worked on the identifying trust levels code | Finish coding the c++ coding inside the added project | none
23/1/2018 | Jude | I was on leave yesterday, so couldn't do anything | finish the documentation work with team, finalize the previous C++ codes | None
| Sajith | Fixed one existing issue in the C++ project | Finalize the documentation for indirect trust calculation | none
| Sandunika | Worked on IT documentation | complete the direct trust c++ implementations | none
| Anushka | Worked on the indirect trust calculation documentation. | Finalize the c++ code for the identifying trust levels, Complete the documentation for indirect trust calculation documentation with the team. | None
24/1/2018 | Jude | Went through the direct trust integration to a one single main function | Integrate the 2nd 3rd algorithms into the main function | None
Sajith
| Sandunika | completed the ditect trust calculation c++ code | solve TFS issue | none
| Anushka | Implemented the code for identifying trust levels, Tried to resolve the TFS issue. | Resolve the TFS issue and integrate the project. | An issue with TFS was risen (Team Foundation Server)
25/1/2018 | Jude | went through the trust level classification code and refactored some of it with anushka | complete the GSoC project proposal and send it to ns-3 community, refactor the remaining part of the trust level classification algorithm with anushka | None
| Sajith | because of my bad health lost my courage to continue on this | since now getting recovered need to complete missing targets by integrating spiral code and take some few steps forward to move into the right track | none
Sandunika
| Anushka | Implemented the code for identifying trust levels, Resolved the TFS issue | Finalize the code for identifying trust levels. | none
26/1/2018 | Jude | Discussed about the classification algorithm with Anushka and explain the modifications needs to do | Do the hangout session for today's work, Complete the remaining integration work for classification algorithm | None
| Sajith | Implemented spiral c++ code again upto some extent | Complete the rest with the integration | None
| Sandunika | Modify the code to add direct trust value to the indirect trust table | Complete the integration | None
Anushka
27/1/2018 | Jude | checked the TFS problem with the team | completed the 4th algorithmn C++ code | None
| Sajith | Worked in the integrated c++ project to fine tune the spiral code | Finalize c++ project with team members | None
Sandunika
| Anushka | Fixed the update of the trust level for trust table, Started working on entering records to recommendation table | Finish the remaining methods regarding recommendation table | None
28/1/2018 | Jude | Went through the after transmission phase and wrote the C++ code, Check the GSoC project idea status | refactor more 4th algorihtmn code, Come up with a solution for another broadcast message sending mechanism | None
| Sajith | Checked in the Spiral c++ code to TFS | Move into ns3 source code | None
Sandunika
| Anushka | Fixed adding values to the recommendation table | Work on the reduction factor method | None
29/1/2018 | Jude | Couldn't do any work | Do a Google Hangout session to solve the existing blockers, Start integrating the current code to ns3 | None
| Sajith | Couldn't do much work today | Work in ns3 | Ns3 environment was still unfamiliar to me.
| Sandunika | implemented the scaling function for Direct trust between 0 - 1, Did modifications regarding adding rreq , rply ... values to calculate direct trust | work on ns3 | none
| Anushka | tried to resolve the issue of getting recommendation value to the recommendation table | figure out a way to send the DT from one node's trust table to another node's recommendations table | Still have the above issue to be solved. Can't move forward without doing so.
30/1/2018 | Jude | integrated the C++ code into ns=3 source code with other team members | fix the existing integration issues | None
| Sajith | Integrate implemented algorithm to ns3 project | Fix existing issues in the integration | None
| Sandunika | did modifications to Direct trust code in ns3 project | go through ns3 project and find a way to send rreq | none
| Anushka | implemented the method for sending request for GT of another node's trust table and receive it. | make necessary modifications to the above method, add it to the integrated project | none
31/1/2018 | Jude | Checked the issues with building ns-3, identified that there is a encoding problem with the new classes we have added | continue with fixing the existing build problems in ns-3 with our new class files | None
| Sajith | Fixed some build issues in ns3 with team members | Complete the process of fixing build issues in ns3 | None
| Sandunika | Went through ns3 code and participated for fixing build issues | Find a way to implement rreq | None
Anushka
2018-01-02 | Jude
| Sajith | Fixed all the existing issues in ns3 building process with our implemented algorithm | Start to run our implemented algorithm. | None
Sandunika
| Anushka | cloned the project and tried to build and run it, cloned the project and tried to build and run it. | clone, build and run the latest error free version, Add the above solution to the NS3 project | none
2018-02-02 | Jude | Worked on the document, explain the achievable target to each member | Try to understand the existing routing protocol procedure and get more idea on it | None
| Sajith | Worked on the documentation with team | Fix issues which are coming from when integrating our entire C++ project | None
| Sandunika | worked on documentation, Went throught netAnim | Apply netAnim to ns3 code and try to visualize it | nonr
| Anushka | Started going through the AODV routing protocols files. | Go through the AODV routing protocols methods more and figure out a way to send TRR based on those methods. | none
2018-03-02 | Jude
| Sajith | Added some missing files to aodv-trust module and integrated | Further proceed with our implemented algorithm and RoutingProtocol class in ns3 | none
| Sandunika | went throught netAnim and got some issues while running the project | solve existing issues and go through routing protocol classes | None
| Anushka | Went through send hello and receive rreq methods to understand how the interaction between two nodes happens | Try to Implement a similar method to send TRR | none
2018-04-02 | Jude
| Sajith | Couldn't do much work today | Go with aodv-trust module in ns3 | none
Sandunika
Anushka
2018-05-02 | Jude
Sajith
| Sandunika | Commited the changes added to the code, Went through routing protocols | Went through the code and find a way to execute RREQ and rply methods | none
| Anushka | Went through the aodv protocol methods a bit more, Installed git bash and committed the small changes I had done to the code. Recalled memory on working with git. | Participate to the call tonight and help with finishing what's left on calculating direct trust, Start working on method to send TRR | none
2018-06-02 | Jude | Briefly checked some code which has committed | Implement the direct trust calculation part into the protocol | None
| Sajith | Identified the execution order of methods inside aodv-routing-protocol.cc and did a hangout session | Find the best place to integrate our code. | Since I had to use cout instead of debugging it was a tedious task to identify with large amount of data in the terminal
Sandunika
| Anushka | Created a dev branch and committed direct trust changes to the dev branch. | Watch the hangout session and understand the execution order of aodv routing protocol methods | None
2018-07-02 | Jude | Cloned the new branch from git, Tried to integrate the direct trust calculation into the protocol | Figured out that all Singleton objects needs to be refactored, Go through the hangout session done by Chamara | None
| Sajith | Removed Singleton pattern from TrustTable and Recommendation Table classes | Removed it from BackupTable class as well | Removing Singleton pattern from BackupTable attempt was failed. So I will give a new try.
| Sandunika | Went through the aodv routing protocol files along with hangout session | Completely understand the flow of aodv-routing protocol | None
| Anushka | Watched the hangout session and got to know the order of methods execution, Removed the singleton classes added | Pull the latest version of the project and study the output | none
2018-08-02 | Jude
Sajith
| Sandunika | went through the routing protocol and rreq method | complete direct trust and try to use rreq in that | none
| Anushka | Removed the NodeEntry class and instead of that, added the node's ip address directly as am attributes to the trust table, Edited the rest of the project according to the above mentioned change | Fix the error which occurred regarding direct trust methods after editing | none
2018-09-02 | Jude | had the weekly supervisor meeting, corrected the cout logs in the code | complete the trust table integration to the existing code with others | None
| Sajith | Tried to find a way to fix redefinition build failure in BackupTable classes | Find how other team mates move forward in ns3 | none
| Sandunika | fixed the error with direct trust implementation | Go through rreq , rply , hello , err methods more | none
| Anushka | Fixed the merge conflicts and the remaining error from yesterday after removing NodeEntry class, Committed all the changes to git | Install tortoise git on Ubuntu and start committing through that, Work on figuring out how the messaged between two nodes are to be sent | none
2018-10-02 | Jude | Pulled the latest changes from the repo and checked for any build errors, Added the trust tables into the routing protocol | Complete the direct trust calculation pararel to the protocol execution | None
| Sajith | Resolved the existing issues in BackupTable related classes by removing Singleton and commited to our repo, Went through the code which others committed previous days | Discuss with my team and make a plan and execute to be true for complete the rest of the ns3 implementations | none
| Sandunika | went through rreq flow and noted special points | continue working on data packet sending | none
| Anushka | Didn't get to do much work since I got injured. | Work on figuring out how the messaged between two nodes are to be sent | none
2018-11-02 | Jude | Went through the code and refactored some classes, Removed unnecessary commented blocks, Found a place which might be useful to find the neighborhood nodes | Prepare the gsoc proposal, Start the research paper writing | None
Sajith
| Sandunika | Modified metadatatoolkit class and add some changes to the routing-protocol.cc regarding direct trust | Add the registered ipaddresses to the trust table | none
| Anushka | Downloaded and installed smartgit for Ubuntu, Searched for a way to retrieve the ip address of a device connected to the router port | Find a way to add the connected devices to a router's trust table | none
2018-12-02 | Jude | went through the methods which can retrieve the neighbor nodes of a router, had a meeting with Chamira miss about gathered some points to include in the GSoC proposal | create the project proposal for gsoc | none
| Sajith | Removed TestValueGenerator class and allow to print the routing table, Tried out a way to find the one hope neighbors | Start writing research paper | none
| Sandunika | Went throught research paper structure, Went through routing-protool and tried to get one hop neighbours to the trust table | start writing research paper | none
| Anushka | Went through the research papers and planned the structure of how ours should be written. | Start writing the research paper. | none
13/2/2018 | Jude | Did some pages in the gsoc project proposal creation | Have a hangout session with the others to add the record to trust table | None
Sajith
Sandunika
| Anushka | Implemented a method retrieve neighbor nodes from routing table and to insert them in to the trust table | Finalize the above mentioned method. | none
14/2/2018 | Jude | had a discussion with anushka about identifying the neighbour nodes and add them to the trust table, tried few methods which might be the correct places to do that operations, but couldn't succeed | try to fix identify the correct place and fill the trust tab;e | none
| Sajith | Tried out a way to visualize behaviors of aodv-routing protocol using netanim | Complete above mentioned attempt and move forward with the team | None
| Sandunika | went through updating routing table methods | Try to calculate direct trust for routing table node entries | none
| Anushka | Completed the method for populating trust table with routing table node entries. | Use the above method for trust table calculation and remove the dummy trust table value generation. | None
15/2/2018 | Jude
| Sajith | Visualize aodv-routing protocol simulation using netanim | Go through which Anushka has committed and move forward with that code | Unable to set cordinations for nodes without packet loosing in netanim
Sandunika
| Anushka | double checked everything I had done and committed for others to continue their work with | Change identifying trust levels method according to the newly added methods | None
16/2/2018 | Jude | couldn't do much work | do the google hangout session with the team | none
| Sajith | Went through the code which Anushka has committed | Discuss with the team to get clarified and optimize that implementation | None
| Sandunika | went through the code and tried to find a suitable place to add the new method | Have a call with teammates and solve existing issues | None
| Anushka | Couldn't do much work. Traveling took most of the day. | Have a Skype call with the team and figure out the remaining issues | none
17/2/2018 | Jude | removed the unnecessary logs and understood the flow of the methods which are being called, did a hangout session, but due to connectivity issues, couldn't cover the entire session | find a way to debug the program, raise the question to ns-3 community about identifying the neighbour nodes | none
| Sajith | Had a meeting with supervisor and the team | Find a way to add the missing nodes to trust table which are listed in routing table | Unable to find a way to add missing entries yet by following the routing table add method. So hoping to try out add only that missing entries in another place
Sandunika
Anushka
18/2/2018 | Jude | Searched how to debug ns-3, Went through to find a way to get the neighborhood nodes | Debug the ns-3 and see the runtime values | None
Sajith
| Sandunika | Went through the code and tried to find all the neighbour nodes | Go through debugging | none
Anushka
19/2/2018 | Jude | went through the blogs to debug ns-3 | try to debug the program | none
| Sajith | Start writing the project charter | Debug the program to see runtime values | None
Sandunika
| Anushka | Removed the couts used to identify the execution order of methods, Called the populate trust table method on a specific place and committed, Went through the project charter and started filling some details | Complete the project charter, Discuss further details about debugging through Skype call and figure out the reason for missing out some entries in the trust table | none
20/2/2018 | Jude
Sajith
Sandunika
| Anushka | Removed the MetaDataToolKit class and added all its functionalities tp the trust table, Finalized the method to populate the trust table and fixed the issue of missing out some neighbor node entries | Fix the issue of packets not being incremented in the table for method calls | None
21/2/2018 | Jude | Looked into the existing problem of counter values aren't being updated in the trust table record | Find out a way to debug the ns3 | None
| Sajith | Worked on project charter, Went through the existing issue in incrementing rreq | Complete the charter | In the existing implemented ns3 project rreq is incremented at the very beginning only once by node 0
| Sandunika | Tried to solve the issue for rreq increment, worked on project charter | Complete project charter | none
| Anushka | Tried to figure out the issue with increments on the trust table with the team | Change identifying trust levels method according to the current trust table that's used and it's values | none
22/2/2018 | Jude | Wrote the workload for member 1 and member 2 in project charter document | complete the project charter document, start writing the GSoC project proposal | None
| Sajith | Couldn't do much work | Complete the project charter | None
Sandunika
| Anushka | Filled information in the project charter with the team | Complete the project charter | none
23/2/2018 | Jude
| Sajith | Completed the project charter with team | Work on ns3 again | none
| Sandunika | Worked on project charter | continue work in ns3 | none
Anushka
24/2/2018 | Jude
| Sajith | Found a way to get the number of RREQ and add it to Trust Table, Tried to get the number of reply and add it to Trust Table | Find a way get reply, hello, err count as well | Unable to find a better place to get the rply count yet
Sandunika
Anushka
25/2/2018 | Jude
| Sajith | Completed adding count variables to trust table for calculating control packets | Complete the implementation of data packets transmission | None
Sandunika
| Anushka | Completed trust table and updating all its methods with the team, Started implementing the simulator | Complete the packet forwarding and receiving counts, complete the simulator | None
26/2/2018 | Jude | Implemented the control packet counters and maintained those values with the help of team members, Created an data packet simulation with anushka | Start implementing send TRR message to get the recommendation values | None
Sajith
| Sandunika | went through the modifications in trust table | Work on sending TRR message | none
| Anushka | Resolved the issue and Incremented NDF,NDR successfully, Called calculating direct and indirect trusts and made the modification for them to be updated in the table correctly, Worked on the Interaction count increment with jude, Created the method for populating recommendation table | Work on sending the TRR with the team, Populate the rest of the columns in recommendation table | none
27/2/2018 | Jude | Had a progress status meeting with the team, Define goals for everyone, Looked into sendTRR method implementation location in the code | Fix the issue with sending the TRR with the help from Anushka | None
| Sajith | Figured out the issue of printing same value for indirect trust in visual studio code, Start writing the introduction part of proposal | Add the fixed issue in indirect trust calculation code to ns3, Work in netanim with Sadunika | None
| Sandunika | Tried to visualize the nodes using netanim | continue work in netanim | none
| Anushka | Created a class for the TRR header and implemented necessary methods, Called the implemented method Inside aodv routing protocol. | Complete procedure of sending the TRR packet | None
28/2/2018 | Jude
| Sajith | Wrote literature review in the proposal | Work in netanim with Sadunika | None
Sandunika
| Anushka | Tried to fix the issue with maturity level not being updated. | Fix the maturity level update in the recommendations tables, Fix sending TRR with the team | none
2018-01-03 | Jude
| Sajith | Worked in netanim and pyviz with Sadunika | Find a way to visualize all the behaviors of nodes | When visualize using pyviz one node get disappeared during the simulation later
| Sandunika | worked in netanim and tried pyviz to visualize nodes | try to solve the probkem with the disapear of one node while visualizing | None
| Anushka | Implemented sendTRR and recvTRR methods with jude, Made some changes to indirect trust calculation class. | Resolve the issue with TRR packet after discussing with Ms. sameera. | None
2018-02-03 | Jude
| Sajith | Couldn't do much work today | Find a solution for yesterday pyviz issue | None
Sandunika
| Anushka | Edited the proposal doc, Went too meet Ms.chameera and discussed about a possible solution for the TRR issue | Start implementing the solution suggested | None
2018-03-03 | Jude
| Sajith | Update the literature review part in the proposal | Discuss with the team to plan the next week of the project | None
| Sandunika | Tried to solve the problem with pyviz visualizer | work in project proposal | none
Anushka
2018-04-03 | Jude | went through the existing problem we had with the TRR receive implementation and discussed it with miss, Identified a solution to overcome the problem | implement the RecvTRR() according to the correct way | None
| Sajith | Couldn't do much work today | Work on the proposal | None
Sandunika
Anushka
2018-05-03 | Jude | Discussed about the solution, Merged the dev branch to master | Implemente the changes | None
| Sajith | Updated the literature review part in the proposal | Work on the rest of the document | None
Sandunika
Anushka
2018-06-03 | Jude | Implemented the basic methods in a new class, Introduced a new table to hold the recommendation values | Solve the existing build errora | None
| Sajith | Refactored and added objectives to proposal document | Complete the refactoring of the proposal doc | None
| Sandunika | Work on TRR method with the team | write the propsal document | nonr
| Anushka | Implemented the TRR methods further with the team, Added a TRRHandler class and a table to maintain TRR data | Focus on finalizing the TRR methods, Edit the proposal document | None
13/3/2018 | Jude | Resolved the build errors and merged the code into master branch, Reviewed the project proposal document | Check the sendTRR functionality | None
| Sajith | Read new research papers and added some important parts under literature review, Discussed with Chamira miss on the project proposal | Edit proposal according to feedback given by miss, Try add some more research papers | None
| Sandunika | Searched more research papers | write the proposal with new research papers | none
Anushka
14/3/2018 | Jude | Went through the code to figure out the scheduling place to calculate the indirect trust, Started to create gsoc proposal | Figure out the proper place to schedule the indirect trust calculation | None
| Sajith | Updated the content of research gap and the problem in proposal | Add another research paper content for the literature review | none
Sandunika
| Anushka | Fixed some of the errors from the modified code regarding sending TRR | Fix the remaining error, Work on the proposal document | None
15/3/2018 | Jude | Worked on the gsoc proposal | Complete the indirect trust calculation | None
| Sajith | Gathered information about scalability research paper | Added another research paper content for the literature review | None
Sandunika
Anushka
16/3/2018 | Jude | scheduled the indirect trust calculation, but the trust table values aren't still getting updated | go through the proposal and refine it further | None
| Sajith | Add the research paper content from scalability maturity based model | Add another research paper content for literature review | None
Sandunika
Anushka
17/3/2018 | Jude
| Sajith | Couldn't do much work today | Add another research paper | None
Sandunika
Anushka
18/3/2018 | Jude | Went through the code and figured out that receive trr is not working as expected | Do a root cause analysis for not receiving trr and come up with a solution | None
| Sajith | Gathered information from a research paper | Added another research paper content | None
Sandunika
Anushka
19/3/2018 | Jude
| Sajith | Added the secure routing with aodv research paper | Try to add another research paper | None
Sandunika
Anushka
20/3/2018 | Jude | Went through the gsoc proposals, Started the documentation section in the porposal | Submit the sample draft of the gsoc proposal | My laptop charging cable broke, therefore I cannot proceed with the aodv code work
| Sajith | Added the trusted AODV research paper | Edit the proposal | None
| Sandunika | Tried to improve the exciting pyviz visualization | Go through more tutorials about pyviz | none
Anushka
21/3/2018 | Jude | Couldn't proceed with any work as much laptop has broken. | submit the GSoC proposal, investigate the root cause for not receiving the TRR response | None
| Sajith | Added the EBoX and Qos research papers | Try to add another research paper | None
Sandunika
Anushka
22/3/2018 | Jude | Worked on the gsoc proposal and submitted for review | Do the modifications which suggested by the mentor on the proposal, Investigate on the receive trr method | None
| Sajith | Tried out pyviz visualization | Edit the proposal | None
Sandunika
| Anushka | Started to fix an error in the current code in dev branch, Read the added sectiona documentation | Resolve the error and commit the code, Work on the documentation more. | None
23/3/2018 | Jude
| Sajith | Started editing objectives | Refactor the proposal according to feedback given by miss | None
| Sandunika | went through the research papers added in documentation | get the vm from sajith and try pyviz visualizer | none
| Anushka | Fixed a couple of runtime errors in the project and committed them. | Resolve the remaining error, Help completing the documentation | none