## Sheet1
Date | Name | Since last meeting | Before next meeting | Blockers
22/12/17
| Jude | went through the diagrams. Started to write the algorithms for the very first flow chart provided by miss | finish the basic algorithm for the first flow chat | None
| Sajith | learned AODV, ns-3, DT, IT and research paper. All were just upto some extent. | hope to dual boot machine with Ubuntu because old laptop had some issues in Ubuntu | None
| Sandunika | went through the diagrams. | complete first pseudo code. | UEE final project
| Anushka | Went through the flow chart on direct trust calculation and went through the research paper. | Work on the algorithm for the first flow chart. Look up on reinforcement learning. | Had to work on the UEE project submission which is due tomorrow (23rd Saturday)
23/12/17
| Jude | went through the remaining algorithm | write the completed pseudo code | None
| Sajith | went through research paper | start writing psuedocodes | None
| Sandunika | wrote the first pseudo code | complete pseudo codes for 2nd and 3rd algorithms and watched videos given by sir | None
| Anushka | Worked on the algorithm for the first flow chart, went through the research paper more and looked up on reinforcement learning | finish the pseudo code for the first flow chart, look up on Q-learning | None
24/12/17
| Jude | Had a meeting with all group members to discuss about the algorithms and finalized those | there is one last psudocode remaining for "After transmission phase"; need to complete it | there are some minor points I encounted while writing some algorithms. Need to get clasrified those
| Sajith | watched some ns3 videos. Discussed and wrote some psuedocodes | After transmission phase psuedocode has to complete | need to clarify flow chart doubts
| Sandunika | watch some python videos. Read Q learning research paper | Learn more about AD Hoc networks Go through research paper more | none
| Anushka | Helped with writing the pseudo code for for first , second and third flowcharts. Started working on the pseudo code for the fourth flowchart. | finish the pseudo code for the fourth flow chart. Go through machine learning videos | While writing the algorithms. Came across points which need further clarification.
25/12/17
| Jude | I couldn't do any work today, as I was busy with Christmas celebration all around me | help to refine the 4th pseudo code and complete it | Clarifications need to get from Chamira miss about what we have raised yesterday
| Sajith | wrote last psuedocode | ns3 implementation stuff need to go through | had an outing
| Sandunika | went through research paper | go throught python videos | none
| Anushka | Wrote the algorithm for the fourth flowchart (Not perfect yet). Watched some Python tutorials. | Finalize the algorithm for the last flow chart. Watch further tutorials on related topics. | Came across some doubtful areas in the last flowchart.
26/12/17 | Jude | Went through the old diagrams and check if there are any further improvements | complete the 4th pseudo code, Modify the old diagrams according to the answers for our questions we had | None
| Sajith | set up the environment for run ns3, went through the answers by sir and miss | complete psudocodes | none
| Sandunika | watch some python videos | go through research papers | none
| Anushka | Got Ubuntu installed Went through the answers provided for the issues we had | Finalize algorithms | none
27/12/17 | Jude | Went through some of the machine learning tutorials, had a samll discussion about the 4th psudocode | find out the problems within the existing psudocodes and try to make them correct if we could find any faults. | None
| Sajith | play around with ns3, went through the last psudocode which was discussed yesterday | need to move bit depth in psudocodes plus ns3 | none
| Sandunika | installed ubuntu, wenr through 4th psudocode | go through ns3 installing process | none
Anushka
28/12/17 | Jude | Went through the pseudo codes and tried to clear out the doubts , participated for the meeting with the supervisor and discussed more about the written pseudo codes and get verified by them | Do the modifications for those pseudo codes with the teammates, start making the document about the the algorithms we have written with some explainations | none
| Sajith | went through the diagrams with new modifications | go through IT calculation and design diagram with teammates, start documenting | none
| Sandunika | none (had a busy day at work. I'll cover extra work tomorrow. ) | go through ns3 installation procesd. Work on pseudo codes | none
| Anushka | Went through the content of the discussion took place today with the supervisor | Make the necessary changes to the algorithms and finalize them | none
29/12/17 | Jude | Start going through the research papers and trying to understand the remaining model | finalize the 4th pseudo code, Finalize the other 3 codes, Read the research papers | None
| Sajith | wrote 4th psudocode | complete documenting | None
| Sandunika | Write the pseduo code for modified 4th diagram | Complete the Q learning research paper | none
Anushka
30/12/17 | Jude | refined the after transmission phase pseudo code, installed the visual studio IDE, started to write transmission code in C++, prepared the document which includes all 4 pesudo codes with a description of what each code does (as a group work) | finalize the document content, read and understand about the research papers in-depth, write the remaining C++ codes | None
| Sajith | started to write spiral code in C++, prepared the doc as a team work | read the research paper to get a more idea about the IT calculation process | None
| Sandunika | started to write DT calculation code in C++, participated for documentation | go through research paper, complete c++ code | none
| Anushka | Wrote the pseudo code for identifying trust levels according to the research paper standard, Started the c++ coding for identifying trust levels for a node, Did the documentation part for identifying trust levels | Install NS3 , Complete the c++ code | None
31/12/17 | Jude | Read the first research paper, Had a discussion with other members about the second research paper | finish the remaining section in the research papers, Write C++ codes | None
| Sajith | Read the second research paper, Had a discussion with other members regarding first research paper | Finish reading the second research paper, Continue c++ code | None
Sandunika
Anushka
2018-01-01 | Jude | I couldn't do much work except reading the remaining pages of the 1st research paper | Finish reading papers, Have a discussion with the other members, Try to come up with a flowchart for indirect trust calculation | None
| Sajith | read the research paper | start coding | None
| Sandunika | complete the Q-learning research paper, Go through some c++ tutorials | complete second research paper | none
| Anushka | Went through the research papers | Go through research papers more , Go through NS3 tutorials | None
2018-02-01 | Jude | Went through the research paper, Wrote some remaining section of the 4th algorithm in C++ | Come up with a sketch for the indirect trust calculation | None
| Sajith | went through C++ video | complete spiral C++ code | None
| Sandunika | complete the Q-learning research paper, Go through some c++ tutorials | read research paper, Go through c++ tutorials | none
| Anushka | Went through the research papers, went through NS3 tutorials | Complete the c++ codes | None
2018-03-01 | Jude | Went through the C++ codes, Started the discuss about the 2nd research paper within the group | Finish reading the 2nd research paper, Have an Google hangout session for the introduction of the NS3 codebase | None
| Sajith | went through C++ tutorials | complete C++ code | None
| Sandunika | start writing c++ code, Went through research paper | read research papers, Complete c++ code | none
| Anushka | Went through the discussion notes noted by the group about Axioms | Complete the c++ codes, Go through the tutorials | None
2018-04-01 | Jude | Discussed about the 4 aximos and the 2 models proposed by the 2nd research paper | have the NS3 introductory session about the module structure | None
| Sajith | started C++ implementing | go through ns3 tutorials | none
| Sandunika | Watched c++ tutorials, Study aout 4 axioms | Complete c++ code, read research papers | none
| Anushka | Went through c++ tutorials and implemented most of the code | Complete the c++ code | none
2018-05-01 | Jude | Went through the remaining section in second research paper, Did a introductory session for ns3 | Watch the NS3 YouTube videos, Start to getting familiarize with ns3 code | None
| Sajith | Implementation completed upto some extent | Watch NS3 tutorials | None
| Sandunika | Completed c++ code for DT calculation | watch ns3 tutorials, Read research paper | none
| Anushka | Started watching NS3 tutorials, Changed the implemented c++ code for algorithm 2 by including classes | Watch NS3 tutorials | none
2018-06-01 | Jude | Started to watch the YouTube video series, Built a small network topology along with the tutorial guide | Watch the aodv videos, Get basic idea about NS3 classes for creating a small network | None
| Sajith | went through ns3 tutorials | get an idea about ns3 project structure | None
| Sandunika | watched ns3 tutorials | Cotinue watching ns3 tutorials | none
| Anushka | Watched NS3 tutorials, Made more changes to the implemented c++ code | Watch more NS3 tutorials, Finalize the changed c++ code | None
2018-07-01 | Jude | Watched the youtube videos about ns3, created a small network topology by following up those tutorial series, started to observe a bit about the aodv module folder in ns3 | Do another hangout session with the findings in the aodv module code in ns3 | None
| Sajith | Went through ns3 | Fix building issues of migrating from ns3.26 to ns3. 20 | None
| Sandunika | watched ns3 tutorials, Went through ns3 installation process further | successfully install ns3, Build network by following tutorials | none
| Anushka | Went through AODV and gathered information to be presented on the next hangout session | Get more familiar with NS3, Explain about AODV to the rest of the members | none
2018-08-01 | Jude
| Sajith | Fixed the build issue of migrating from ns3. 26 to ns3. 20, Created a network topology upto some extent | Go through ns3 ahead | none
Sandunika
| Anushka | Installed the suggested version of NS3 successfully and went through it, Watched an NS3 tutorial and tried it on | Try out more tutorials on NS3 and get familiar with it | None
2018-09-01 | Jude | Started to look into the aodv prototal code implementations | provide an feedback to sir with the investigation findings on existing aodv protocol implementation | None
| Sajith | Went through ns3 tutorials, Went through project structure a bit | Configure things according to our research project | None
| Sandunika | tried out ns3 tutorails | find more ns3 tutorials and try them | none
| Anushka | Watched more NS3 tutorials and tried them | Keep on watching more tutorials and try them, Look further in to adding applications | None
2018-10-01 | Jude | Went through the aodv protocol example, Identified some class flows | Do a hangout session about the class structures which related to aodv protocol | None
| Sajith | Went through AODV module in ns3 | Try to find the place where we should call our implemented c++ code last week | none
| Sandunika | Went through aodv prototal code implementations | Go through the aodv code further and try to understand unclear parts | none
| Anushka | Went through AODV module in the NS3 code | Try to figure out where to make the decision when sending packets | None
2018-11-01 | Jude | Went through the code and identified how a protocol is being plugged to a simulation | Do the google hangout session about the knowledge gathered so far, Continue to surf in the ns3 code | None
| Sajith | Played around with aodv.cc | Go through ns3 code moreover | None
Sandunika
| Anushka | Went through AODV example class and other references and tutorials. | Participate to the session and Learn how the protocol plugs ins to a simulation, Go through AODV more | None
2018-12-01 | Jude
| Sajith | Got an idea about aodv sample file | Go through dsdv sample file get more idea about aodv | None
| Sandunika | Went through AODV sample files | Go through the code more and have an idea about dsdv files | none
| Anushka | Participated in the AODV hangout session and got an idea about it, Went through the video again | Check out dsdv and dsr files as well. | None
13/1/2018 | Jude | Went theough the Scheduler engine in NS3, Went through the code examples | Start writing the new protocol file | As the scheduler engine is more complex when it comes to identifying the overall procedure, decided to move on implementation
| Sajith | Went through ns3 documentations | Start implementing in ns3 | None
| Sandunika | went through ns3 code examples and documentation | start implementations | none
Anushka
14/1/2018 | Jude | Went through the code and started to create a new protocol file and tried to test it | Resolve the existing problem with ping is not being working with the new protocol file | None
| Sajith | Experimented aodv sample file | Create a new module in ns3 and try out | None
| Sandunika | went through the aodv helper classes more | Try to create the new protocol file | none
Anushka
15/1/2018 | Jude | Went through the errors encountered while building the module and fixed them, Explained the current progress to all members and clarified the doubts, Posted a new post on ns3 Google group about the gsoc 2018 which related to this project | Observe the existing routine table interactions and try to figure out a way to implement the trust table | None
| Sajith | Created a new module in ns3 which is same as aodv with team mates | Start coding in new module | none
Sandunika
| Anushka | Went through the added new NS3 module, Went through the code with the group members and discussed | Figure out how routing table works, Try to implement the code inside the new module | none